REBMA IMPEX GHANA LIMITED

Operational Management System

Full Project Plan & Architecture

Version 1.1   |   April 2026

| 8 Departments | 38 Features | 5 Sprints | 18 Weeks |
| --- | --- | --- | --- |

# 1. Company Overview

| Company | REBMA IMPEX Ghana Limited |
| --- | --- |
| Products | Milk powder, flour, margarine — imported and locally distributed |
| Suppliers | Poland and Turkey — international payments in foreign currency |
| Distribution | Local delivery by GPS coordinates across Ghana |
| Staff | 100+ workers across 8 departments — concurrent system users |
| System type | Web application — Next.js, hosted on Vercel + Supabase cloud |
| Builder | Developer + AI tools (Claude, Cursor, v0) |

# 2. Departments (Final — 8 Total)

CEO and Manager share one dashboard layout. Role controls what each sees inside it. Every feature is a component with an allowedRoles config — add or remove access without rebuilding.

| 01 — CEO & Manager ¦ /dashboard/management |  |  |
| --- | --- | --- |
| Feature | Description | Sprint |
| Approval queue + thresholds | Manager — credit sales and expenses only | S1 |
| Import approvals | CEO only — all imports route directly to CEO queue | S1 |
| International payments | CEO only — supplier payments to Poland and Turkey | S1 |
| CEO override | CEO can override any Manager decision | S1 |
| Audit log viewer | CEO + Manager — read only, immutable | S2 |
| Live GPS map | CEO, Manager, Supervisor, Dispatch head, HR head | S2 |
| FX rate log | CEO logs rate per international payment. Finance reads only. | S3 |
| Executive dashboard | CEO — read-only summary of all 8 departments | S4 |

| 02 — Finance ¦ /dashboard/finance |  |  |
| --- | --- | --- |
| Feature | Description | Sprint |
| Invoice generator | Auto on order confirm. PDF export via React-PDF. | S1 |
| Payment recording | Cash + transfer. Concurrent-safe with row locking. | S1 |
| Daily reconciliation | Auto midnight Edge Function. Flags mismatches. | S2 |
| Expense log | Category-based. Routes to Manager approval queue. | S2 |
| FX ledger | CEO-authorised FX rate per international transaction. Finance reads only. | S3 |
| GRA reports | Tax docs, compliance. 7-year data retention. | S4 |

| 03 — Marketing ¦ /dashboard/marketing |  |  |
| --- | --- | --- |
| Feature | Description | Sprint |
| Order entry | Mobile-first, offline PWA. Own customers only. | S1 |
| Customer directory | Own customers only. Name, GPS, contact, risk status. | S1 |
| Order status tracker | Live status updates via Supabase Realtime. | S2 |
| Demand signal | Rep flags product demand for import consideration. | S3 |

| 04 — Operations ¦ /dashboard/operations |  |  |
| --- | --- | --- |
| Feature | Description | Sprint |
| Live inventory | Real-time stock levels per product via Supabase Realtime. | S1 |
| Stock reservation | Atomic PostgreSQL function. Prevents overselling. | S1 |
| Goods receipt | Receive imported goods. Reconcile vs purchase order. | S2 |
| Discrepancy report | Physical count vs system. Auto-alert to Manager + Supervisor. | S2 |
| Supplier vetting | Profiles, reliability score, blacklist. | S3 |
| Import workflow | Demand signal → CEO approval → CEO pays → PO → customs → receipt. | S3 |

| 05 — Production ¦ /dashboard/production |  |  |
| --- | --- | --- |
| Feature | Description | Sprint |
| Repack job cards | Input qty, output qty, assigned workers, start/end time. | S3 |
| Quality check log | Pass/fail per batch. Failed batch cannot be closed. | S3 |
| Packaging inventory | Sachets, bags, cartons, labels, nylon, sealing materials. | S3 |
| Batch to stock trigger | Closing a batch auto-updates Operations stock levels. | S3 |

| 06 — Dispatch ¦ /dashboard/dispatch |  |  |
| --- | --- | --- |
| Feature | Description | Sprint |
| Delivery job board | Dispatcher assigns trips from confirmed orders. | S2 |
| Multi-stop trips | Locked sequence. Stop N+1 unlocks after stop N confirmed. | S2 |
| Driver mobile view | Today's trip only. Offline PWA. GPS + actions per stop. | S2 |
| GPS live tracking | 15-second pings. Journey events. 200m geofence on arrival. | S2 |
| Proof of delivery | Digital signature + GPS coordinates + timestamp per stop. | S2 |
| Vehicle + driver log | Vehicle assignment, mileage, full trip history. | S4 |

| 07 — HR ¦ /dashboard/hr |  |  |
| --- | --- | --- |
| Feature | Description | Sprint |
| Registration approval | New staff registers → HR reviews → approve/decline/more info. | S1 |
| User account management | Create accounts, assign roles, deactivate leavers. | S1 |
| Employee roster | 100+ staff records — dept, role, status, contact, start date. | S1 |
| Attendance | Clock-in/out self-service. HR monitors all staff. | S2 |
| Leave management | Staff requests → Supervisor approves → HR records. | S2 |
| Payroll + payslips | Monthly salary run. PDF payslip per employee. | S4 |
| Training + disciplinary | Training log all staff. Disciplinary: HR head + CEO only. | S5 |

# 3. Roles & Access

5 roles in the system. Supervisor is a role, not a department — belongs to one of the 8 departments with elevated access on top of their department permissions.

| Role | Can do | Cannot do | Count |
| --- | --- | --- | --- |
| CEO | Read everything. Approve imports. Authorise international payments. Log FX rates. Override Manager. GPS map. Audit log. | Cannot manage day-to-day approval queue. Cannot change system config. | 1 account |
| Manager | Approval queue — credit sales and expenses. Set thresholds. System config. Alerts. GPS map. | Cannot approve imports. Cannot authorise international payments. | 1–3 |
| Supervisor | Below-threshold approvals. Cross-dept read. Operational alerts. GPS map. | Cannot set thresholds. Cannot access salary data. Cannot override Manager. | 2–5 |
| Dept Head | Full access own dept. Read from dependent depts. Approve own staff leave. | No write access to other depts. No salary data (except HR head). | 8 |
| Staff | Own records only. Self-service: attendance, leave, payslip. | No cross-dept access. No financial records. No other staff data. | 90+ |

# 4. Technology Stack

| Framework | Next.js 14 — App Router, Server Actions, PWA |
| --- | --- |
| Language | TypeScript — strict mode, types auto-generated from Supabase CLI |
| Styling | Tailwind CSS |
| Animation | Framer Motion — transitions, notifications, map movements |
| Database | Supabase (PostgreSQL) — relational, foreign keys, atomic functions |
| Auth | Supabase Auth — email + password. Custom JWT: role + department |
| Security | Row Level Security (RLS) on every table from day one |
| Realtime | Supabase Realtime — approval queue, stock levels, order status, GPS |
| Storage | Supabase Storage — invoices, signatures, docs, payslips, GRA reports |
| Scheduled jobs | Edge Functions — reconciliation, low stock, licence expiry, GPS cleanup |
| Hosting | Vercel (frontend) + Supabase Pro ($25/mo before go-live) |
| GPS / Maps | Google Maps API — live tracking, route, geofence, navigation |
| SMS | Hubtel or Arkesel — Ghana-based, urgent alerts |
| Email | Resend — registration, approvals, account activation |
| PDF | React-PDF — invoices, payslips, GRA reports |

# 5. Sprint Plan

Sprint order is fixed. Auth, RLS, and audit log must exist before any feature is built.

| Sprint 1 — Foundation ¦ Weeks 1–4 ¦ 13 features |  |  |
| --- | --- | --- |
| Feature | Description | Department |
| Auth + role routing | Login, session, middleware, role dashboards | System |
| Audit log trigger | DB trigger on every table. Immutable. Built first. | System |
| Registration approval | Pending → HR review → approve / decline / more info | HR |
| User account management | Create, deactivate, assign roles | HR |
| Employee roster | 100+ staff records | HR |
| Live inventory | Realtime stock levels with RLS | Operations |
| Stock reservation | Atomic PostgreSQL function | Operations |
| Order entry | Mobile-first, offline PWA | Marketing |
| Customer directory | Own customers only | Marketing |
| Invoice generator | Auto on order confirm, PDF export | Finance |
| Payment recording | Cash + transfer, concurrent-safe | Finance |
| Manager approval queue | Credit sales and expenses only | Management |
| CEO import + payment queue | All imports and international payments → CEO only | Management |

| Sprint 2 — Operations ¦ Weeks 5–9 ¦ 14 features |  |  |
| --- | --- | --- |
| Feature | Description | Department |
| Goods receipt | Receive goods, reconcile vs PO | Operations |
| Discrepancy report + alert | Physical vs system count, auto-alert | Operations |
| Order status tracker | Live updates via Supabase Realtime | Marketing |
| Daily reconciliation | Auto midnight Edge Function | Finance |
| Expense log | Category-based, routes to Manager approval | Finance |
| Delivery job board | Dispatcher assigns trips from confirmed orders | Dispatch |
| Multi-stop trips | Locked sequence per stop | Dispatch |
| Driver mobile view | Offline PWA, today's jobs only | Dispatch |
| GPS live tracking + events | 15-second pings, journey milestones | Dispatch |
| Proof of delivery | Signature + GPS + timestamp per stop | Dispatch |
| Unplanned stop alert | 15min stationary → SMS all permitted roles | Dispatch |
| Attendance | Clock-in/out self-service | HR |
| Leave management | Request → Supervisor approves → HR records | HR |
| Audit log viewer | CEO + Manager, read-only | Management |

| Sprint 3 — Supply Chain ¦ Weeks 10–13 ¦ 8 features |  |  |
| --- | --- | --- |
| Feature | Description | Department |
| Import workflow | Demand → CEO approves → CEO pays → PO → customs → receipt | Operations / CEO |
| Supplier vetting | Profiles, reliability score, blacklist | Operations |
| Demand signal | Marketing rep flags product for import | Marketing |
| Repack job cards | Input/output qty, workers, time | Production |
| Quality check log | Pass/fail per batch, fail blocks close | Production |
| Packaging inventory | Sachets, bags, cartons, labels, nylon, sealing | Production |
| Batch to stock trigger | Close batch → auto-updates Operations | Production |
| FX ledger | CEO logs rate. Finance reads for reporting. | CEO / Finance |

| Sprint 4 — Intelligence ¦ Weeks 14–16 ¦ 5 features |  |  |
| --- | --- | --- |
| Feature | Description | Department |
| Executive dashboard | CEO read-only summary of all 8 departments | Management |
| GRA reports + doc store | Tax docs, 7-year retention, searchable | Finance |
| Import licence alerts | 30-day expiry warning — CEO only | CEO / Operations |
| Vehicle + driver log | Assignment, mileage, full trip history | Dispatch |
| Payroll + payslips | Monthly salary run, PDF per employee | HR |

| Sprint 5 — Completion ¦ Weeks 17–18 ¦ 5 features |  |  |
| --- | --- | --- |
| Feature | Description | Department |
| Training + disciplinary log | HR head + CEO only for disciplinary | HR |
| GPS ping cleanup job | Edge Function, 90-day retention policy | System |
| UAT — all departments | Each dept head tests with real data | All |
| 2-week parallel run | System alongside manual process | All |
| Go-live + cutover | Manual process retired. System live. | All |

# 6. Alert System

In-app badge (always) + email via Resend (non-urgent) + SMS via Hubtel/Arkesel (urgent).

| Alert | CEO | Manager | Supervisor | Dispatch head | HR head | Finance head |
| --- | --- | --- | --- | --- | --- | --- |
| Unplanned stop (15min+) | Yes | Yes | Yes | Yes | Yes | — |
| Failed delivery | Yes | Yes | Yes | Yes | — | — |
| New staff registration | — | — | — | — | Yes | — |
| Registration decided | Yes | Yes | — | — | Yes | — |
| Approval pending (credit/expense) | — | Yes | Yes | — | — | — |
| Import approval pending | Yes | — | — | — | — | — |
| Low stock | Yes | Yes | Yes | — | — | — |
| Stock discrepancy | Yes | Yes | Yes | — | — | — |
| Reconciliation mismatch | Yes | Yes | — | — | — | Yes |
| Import licence expiring | Yes | — | — | — | — | — |
| Delivery confirmed | — | Yes | — | Yes | — | Yes |

# 7. Non-Negotiable Build Rules

These rules apply throughout the entire build without exception.

01.  RLS on every table from day one

Never disable, even during development. Security enforced at database level — not just the UI.

02.  Audit log built before any feature

DB trigger on every table. Written automatically. Nobody can edit or delete it. Ever.

03.  Stock reservation is a PostgreSQL function

Never handle concurrency in application code. The database enforces it atomically.

04.  Stock ledger is append-only

No UPDATE or DELETE on stock_ledger. Balance = SUM of all movements. Full history preserved.

05.  Every feature maps to a department

No orphan screens. New ideas go to a backlog — not into the current sprint.

06.  Marketing + Dispatch are offline-first

PWA service worker. Sync queue for offline actions. Non-negotiable for field staff.

07.  Role never comes from the client

Always read from JWT or fresh DB call. Middleware and RLS control access — not the UI.

08.  Salary data blocked at RLS level

HR head and CEO only. The DB query returns nothing for all other roles.

09.  GPS tracks only during active delivery

Starts when driver taps Start. Stops when driver taps Back at base. 90-day retention.

10.  Sprint order is fixed

Sprint 1 complete before Sprint 2 starts. No exceptions.

11.  Upgrade Supabase to Pro before go-live

Free tier cannot handle 100+ concurrent connections. Upgrade at least 2 weeks before.

12.  Run parallel for 2 weeks before cutover

System runs alongside manual process. Retire manual only when system is stable.

REBMA IMPEX Ghana Limited — Operational Management System Plan

Confidential — Internal use only